## Slide 1: The Application of ai in Detecting and Preventing Cyber attacks in Healthcare Organisations
Afry Nizam
PCP
HND in Computing

## Slide 2: Introduction & Project Background
HEALTHCARE ORGANIZATIONS STORE SENSITIVE PATIENT DATA
RANSOMWARE AND PHISHING ATTACKS ARE INCREASING IN HEALTHCARE
AI HELPS TO DETECT CYBERATTACKS FASTER AND MORE ACCURATELY

## Slide 3: Literature Review
AI IMPROVES THE ACCURACY OF CYBER THREAT DETECTION
MACHINE LEARNING HELPS TO IDENTIFY UNUSUAL SYSTEM ACTIVITY
DEEP LEARNING HELPS TO DETECT ADVANCED CYBER THREATS
AI RESPONDS FASTER THAN TRADITIONAL SECURITY SYSTEMS
MAIN CHALLENGES INCLUDE HIGH COST AND DATA PRIVACY ISSUES

## Slide 4: Research Methods Used
MIXED RESEARCH APPROACH WAS USED IN THIS STUDY
PRIMARY DATA WAS COLLECTED USING GOOGLE FORMS
BOTH QUANTITATIVE AND QUALITATIVE QUESTIONS WERE USED
PRIMARY DATA WAS COLLECTED THROUGH SURVEYS AND INTERVIEWS

## Slide 5: Project schedule (gantt chart)
Project Schedule |  |  |  |  |  | 
Task No. | Activity | Start Date | End Date | Duration | Remarks | Adjusted Length
1 | Project initiation and topic selection | 1/1/2025 | 1/7/2025 | 1 week | Research topic finalised and approved | 6
2 | Defining aims, objectives, and project scope | 1/7/2025 | 1/13/2025 | 6 days | Overlaps with initiation for time efficiency | 6
3 | Literature review (secondary research) | 1/13/2025 | 1/27/2025 | 2 weeks | Review of journals, articles, and reports | 14
4 | Research methodology design | 1/27/2025 | 2/2/2025 | 1 week | Selection of qualitative and quantitative methods | 6
5 | Questionnaire development | 2/2/2025 | 2/9/2025 | 1 week | Designing and refining survey questions | 7
6 | Primary data collection | 2/9/2025 | 2/16/2025 | 1 week | Distribution and response collection | 7
7 | Data analysis and interpretation | 2/16/2025 | 2/23/2025 | 1 week | Analysis of primary and secondary data | 7
8 | Report writing | 2/23/2025 | 3/2/2025 | 1 week | Drafting findings, discussion, and conclusion | 7
9 | Review, proofreading, and final submission | 3/2/2025 | 3/9/2025 | 1 week | Final corrections and submission | 7

## Slide 6: Accuracy & Reliability of Methods
STRUCTURED QUESTIONS HELPED TO KEEP CONSISTENT ANSWERS
CHARTS MADE THE DATA EASY TO UNDERSTAND
INTERVIEWS WERE CONDUCTED IN A RELIABLE WAY
USING MULTIPLE DATA SOURCES INCREASED ACCURACY

## Slide 7: CRITICAL REFLECTION
survey had a small number of people, so results may not represent everyone.
Answers were self‑reported, so they may be biased.
Findings should be seen as useful guidance, not final truth.
Future studies should use bigger samples and combine surveys, interviews, and system data.

## Slide 8: Project Planning Decisions
THIS WAS A SMALL-SCALE PROJECT DUE TO TIME LIMITS
HEALTHCARE WAS CHOSEN BECAUSE IT FACES HIGH CYBER RISKS
AI WAS SELECTED FOR REAL-TIME CYBER THREAT DETECTION
GOOGLE FORMS WERE USED BECAUSE THEY ARE LOW COST
PROJECT PLANNING WAS ALIGNED WITH ORGANIZATIONAL NEEDS

## Slide 9: Data Analysis & Key Findings
MOST RESPONDENTS SUPPORT THE USE OF AI IN CYBERSECURITY
AI IS EFFECTIVE AGAINST PHISHING AND RANSOMWARE ATTACKS
FASTER RESPONSE TIME WAS OBSERVED USING AI SYSTEMS
HIGH COST AND LACK OF SKILLS WERE IDENTIFIED AS CHALLENGES

## Slide 10: Challenges Identified
AI IMPLEMENTATION CAN BE VERY EXPENSIVE
THERE IS A SHORTAGE OF AI AND CYBERSECURITY SKILLS
FALSE ALERTS CAN AFFECT USER AND CUSTOMER EXPERIENCE
AI SYSTEMS CAN HAVE ISSUES WITH OLD LEGACY SYSTEMS
REGULATORY AND ETHICAL RULES MUST BE FOLLOWED (NCSC, 2023)

## Slide 11: Project Recommendations
Update AI models regularly
Provide cybersecurity training to staff
Develop strong data protection policies
INTRODUCE AI IN STEPS

## Slide 12: FUTURE IMPROVEMENTS
COLLECT DATA FROM MORE HOSPITALS FOR STRONGER RESULTS
TRACK AI USAGE OVER TIME TO SEE LONG-TERM EFFECTS
COMPARE SURVEY RESULTS WITH REAL SYSTEM DATA
APPLY THIS RESEARCH TO OTHER AREAS LIKE FINANCE AND EDUCATION
USE SURVEYS, INTERVIEWS, AND CASE STUDIES FOR BETTER RELIABILITY

## Slide 13: Conclusion
AI MAKES HEALTHCARE CYBERSECURITY STRONGER
IMPROVES DETECTION AND RESPONSE SPEED
CHALLENGES CAN BE MANAGED WITH GOOD PLANNING
AI IS RECOMMENDED FOR MODERN HEALTHCARE SYSTEMS

## Slide 14: Reference
IBM (2023) Artificial intelligence and cybersecurity in healthcare. Available at: IBM Security Reports.
Microsoft (2023) The role of AI in modern threat detection. Available at: Microsoft Security Blog.
NCSC (2023) Cyber security risks in healthcare. Available at: National Cyber Security Centre.
IBM (2023) Cost of a data breach report. Available at: IBM Security.
https://docs.google.com/forms/d/1dEHWI9ZMiQ9vOTwv9Agkpucw2yM752-9U8zh7

## Slide 15: THANK YOU!